## Sheet1
Diana Obo 13134885 |  | Actual hours spent
Task | Estimate(hrs) | Resources(hrs) | Documenting(hrs) | Coding(hrs) | Total
Generate database | 12 | 0 | 0 | 0 | 0
table for food catalogues | 6 |  |  | 0
table for clothing catalogues | 6 |  |  | 0
Requirements and design documentation | 14 | 0.3 | 0 | 0 | 0.3
Gather functional requirements | 2 | 0.3 | 0 | 0
Functional requirements section | 5 |  |  | 0
Gather architectural requirements | 2 |  |  | 0
Architectural requirements section | 5 |  |  | 0
Admin food interface | 24 | 0 | 0 | 0 | 0
Add functionality in admin food interface | 6
Remove functionality in admin food interface | 6
Update functionality in admin food interface | 6
Add specials functionality in adminfood interface | 6
User food interface | 27.5 | 0 | 0 | 0 | 0
Display price of each item in user food inteface | 5.5
Display price of each item in user food inteface | 5.5
Browse functionality in user food inteface | 5.5
Browse functionality in user food inteface | 5.5
Filter catalogues in user food inteface | 5.5
Admin clothing interface | 24 | 0 | 0 | 0 | 0
Add functionality in admin clothing interface | 6
Remove functionality in adminclothing interface | 6
Update functionality in admin clothing interface | 6
Add specials functionality in admin clothing interface | 6
User clothing interface | 27.5 | 0 | 0 | 0 | 0
Display price of each item in user clothing inteface | 5.5
Display pictures of each item in user clothing inteface | 5.5
Browse functionality in user clothing inteface | 5.5
Search functionality in user clothing inteface | 5.5
Filter catalogues in user clothing inteface | 5.5