## Sheet1
Diana Obo 13134885 |  | Actual hours spent
Task | Estimate(hrs) | Resources(hrs) | Documenting(hrs) | Coding(hrs) | Total
Generate database | 12 | 4 | 0 | 0 | 4
table for food catalogues | 6 | 2 | 0 | 0
table for clothing catalogues | 6 | 2 | 0 | 0
Requirements and design documentation | 14 | 12 | 10.5 | 0 | 22.5
Gather functional requirements | 2 | 1 | 1.5 | 0 | 2.5
Functional requirements section | 5 | 3 | 3 | 0
Gather architectural requirements | 2 | 4 | 3 | 0
Architectural requirements section | 5 | 4 | 3 | 0
Admin food interface | 24 | 10 | 6 | 16 | 32
Add functionality in admin food interface | 6 | 2 | 2 | 2
Remove functionality in admin food interface | 6 | 4 | 2 | 7
Update functionality in admin food interface | 6 | 4 | 2 | 7
Add specials functionality in adminfood interface | 6 | NA | NA | NA
User food interface | 27.5 | 15 | 12 | 14 | 41
Display price of each item in user food inteface | 5.5 | 3 | 3 | 7
Display picture of each item in user food inteface | 5.5 | 3 | 3 | 7
Browse functionality in user food inteface | 5.5 | 3 | 3 | NA
Search functionality in user food inteface | 5.5 | 3 | 3 | NA
Filter catalogues in user food inteface | 5.5 | 3 | NA | NA
Admin clothing interface | 24 | 0.9 | 3 | 3 | 6.9
Add functionality in admin clothing interface | 6 | 0.3 | 1 | 1
Remove functionality in adminclothing interface | 6 | 0.3 | 1 | 1
Update functionality in admin clothing interface | 6 | 0.3 | 1 | 1
Add specials functionality in admin clothing interface | 6 | NA | NA | NA
User clothing interface | 27.5 | 15 | 15 | 4 | 34
Display price of each item in user clothing inteface | 5.5 | 3 | 3 | 2
Display pictures of each item in user clothing inteface | 5.5 | 3 | 3 | 2
Browse functionality in user clothing inteface | 5.5 | 3 | 3 | NA
Search functionality in user clothing inteface | 5.5 | 3 | 3 | NA
Filter catalogues in user clothing inteface | 5.5 | 3 | 3 | NA
Phase 2
Register user Interface | 1 | 0.2 | 0.2 | 1 | 1.4
View user profile interface | 4 | 2 | NA | NA | 2
Update user profile page | 3 | 2 | NA | NA | 2
Login Interface | 2 | 2 | NA | NA | 2
Create Cart icon | 0.3 | NA | NA | NA | 0
View items in cart | 4 | 3 | NA | NA | 3
Add Item into cart | 2 | 3 | NA | NA | 3
Remove item from cart | 2 | 3 | NA | NA | 3
Checkout Items | 3 | NA | NA | NA | 0
List of items bought within sale | 5 | NA | NA | NA | 0